## Gantt
[6 empty] | 24 | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [10 empty] | Reviewers | Dissemination level | Status
[6 empty] | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov
N° | Title | Category | Lead | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | Hybrid Multilinear Modelling | Work package | IWES | 1 | 33
T1.1 | Hybrid Implicit MTI Modeling | Task | IWES | 1 | 14
T1.2 | Model Scalability | Task | HAW | 3 | 14
T1.3 | System Analysis of Hybrid Implicit MTI Models | Task | IWES | 6 | 28
T1.4 | MTI Toolbox Software Development | Task | HAW | 3 | 33
D1.1 | Hybrid Multilinear Model Class and Minimal Format | Deliverable | IWES | 12 | 12 | 2025 Nov: 2 | HAW | PU | Submitted
D1.2 | Alpha Version of the Updated Multilinear MTI Toolbox | Deliverable | HAW | 20 | 20 | 2026 July: 2 | HAW | CO
D1.3 | Final Version of the Updated Multilinear MTI Toolbox incl. Documentation | Deliverable | HAW | 33 | 33 | 2027 Aug: 2 | IWES | PU
MS1.1 | Hybrid iMTI Decomposed Form | Milestone | IWES | 14 | 14 | [36 empty] | HAW |  | Submitted | bar: 24 Dec to 2027 Nov
MS1.1 | Analytic Stability Assessment in MTI Form | Milestone | IWES | 24 | 24 | [36 empty] | HAW | bar: 24 Dec to 2027 Nov
WP2 | Multilinear System Indentification | Work package | HAW | 1 | 30
T2.1 | Improved Multilinearization of Nonlinear Models | Task | HAW | 1 | 12
T2.2 | Multilinear Grey Box System Identification | Task | HAW | 6 | 24
T2.3 | Multilinear Black Box System Identification | Task | HAW | 9 | 28
T2.4 | MTI Model Monitoring and Update | Task | HAW | 6 | 30
D2.1 | Improved Multilinearization Algorithm | Deliverable | HAW | 12 | 12 | 2025 Nov: 2 | IWES | PU | Submitted
D2.2 | Multilinear Grey Box System Identification Algorithm | Deliverable | HAW | 24 | 24 | 2026 Nov: 2 | IWEs | PU
D2.3 | Multilinear Black Box System Identification Algorithm | Deliverable | HAW | 28 | 28 | 2027 Mar: 2 | IWES | PU
D2.4 | MTI Monitoring and Update Algorithm | Deliverable | HAW | 30 | 30 | 2027 May: 2 | IWES | PU
MS2.1 | System Identification in Decomposed MTI Form | Milestone | HAW | 21 | 21 | [36 empty] | IWES | bar: 24 Dec to 2027 Nov
WP3 | Power System Components | Work package | eRoots | 1 | 21
T3.1 | Identification of system components and non-linearities | Task | eRoots | 1 | 5
T3.2 | Conventional power plants and generators | Task | UPC | 3 | 9
T3.3 | Power electronics-based generation | Task | eRoots | 6 | 12
T3.4 | Loads | Task | eRoots | 9 | 12
T3.5 | HVDC, FACTS, and storage | Task | eRoots | 12 | 17
T3.6 | Branches | Task | eRoots | 17 | 21
D3.1 | Report on identified non-linearities and saturations | Deliverable | eRoots | 5 | 5 | 2025 Apr: 2 | UPC | PI | Submitted
D3.2 | Generation multilinear models and validation | Deliverable | eRoots | 12 | 12 | 2025 Nov: 2 | UPC | PU | Submitted
D3.3 | Loads, branches, storage, FACTS and HVDC multilinear models and validation | Deliverable | eRoots | 21 | 21 | 2026 Aug: 2 | UM | PU
MS3.1 | Power System Component Models Completed | Milestone | eRoots | 21 | 21 | [36 empty] | UPC | bar: 24 Dec to 2027 Nov
WP4 | TenSyGrid Toolbox Development | Work package | UPC | 6 | 36
T4.1 | Identification of Use-cases | Task | UPC | 6 | 12
T4.2 | Multilinear tools for power system stability analysis | Task | UPC | 12 | 24
T4.3 | Toolbox framework development and implementation | Task | UPC | 10 | 27
T4.4 | Network analysis applications | Task | UPC | 10 | 36
D4.1 | TenSyGrid Toolbox Applications Roadmap | Deliverable | UPC | 24 | 24 | 2026 Nov: 2 | UM | PU
D4.2 | TenSyGrid Toolbox Framework | Deliverable | UPC | 36 | 36 | 2027 Feb: 2 | eRoots | PU
D4.3 | TenSyGrid Toolbox Applications | Deliverable | UPC | 36 | 36 | 2027 Nov: 2 | UM | PU
MS4.1 | Completed TenSyGrid Toolbox Roadmap | Milestone | UPC | 24 | 24 | [36 empty] | UM | bar: 24 Dec to 2027 Nov
MS4.2 | Completed TenSyGrid Toolbox | Milestone | UPC | 36 | 36 | [36 empty] | eRoots | bar: 24 Dec to 2027 Nov
WP5 | Demonstration and Commercial Feasibility | Work package | UM | 8 | 36
T5.1 | TenSyGrid Toolbox Commercial Software Integration | Task | UM | 8 | 30
T5.2 | Mid-Size Network Model | Task | UM | 18 | 26
T5.3 | Large-Scale Network Model | Task | UM | 24 | 30
T5.4 | Maltese Electrical Network Simulation Case-study | Task | UM | 24 | 36
T5.5 | Malta Feasibility Study Towards 100% Renewables | Task | UM | 28 | 36
D5.1 | Evaluation of TenSyGrid Toolbox Functionalities with test Models | Deliverable | UM | 30 | 30 | 2027 May: 2 | eRoots | PU
D5.2 | Testin with Real-World Examples | Deliverable | UM | 36 | 36 | 2027 Nov: 2 | eRoots | CO
D5.3 | Malta feasibility study towards 100% renewables penetration | Deliverable | UM | 36 | 36 | 2027 Nov: 2 | UPC | CO
MS5.1 | Benchmarking of Toolset | Milestone | UM | 30 | 30 | [36 empty] | eRoots | bar: 24 Dec to 2027 Nov
MS5.2 | Improvement in stability analysis for Real-world case | Milestone | UPC | 36 | 36 | bar: 24 Dec to 2027 Nov
WP6 | Reporting and Knowledge Community | Work package | IWES | 1 | 36
T6.1 | Reporting | Task | IWES | 1 | 36
T6.2 | Formative Evaluation of Project | Task | IWES | 1 | 36
T6.3 | Contribution to Other Knowledge Community Activities | Task | IWES | 1 | 36
D6.1 | First Annual Report | Deliverable | IWES | 12 | 12 | 2026 Jan: 2 | All | CO | Submitted
D6.2 | Second Annual Report | Deliverable | IWES | 24 | 24 | 2026 Nov: 2 | All | CO
D6.3 | Final Report | Deliverable | IWES | 36 | 36 | 2027 Nov: 2 | All | CO
D6.4 | Project Summary | Deliverable | IWES | 36 | 36 | 2027 Nov: 2 | All | CO
WP7 | Management and Dissemination | Work package | IWES | 1 | 36
T7.1 | Project Management and Administration | Task | IWES | 1 | 36
T7.2 | Data Management | Task | IWES | 1 | 36
T7.3 | Results Dissemination, Communication, and Exploitation | Task | IWES | 1 | 36
D7.1 | Project Website | Deliverable | IWES | 4 | 4 | 2025 Mar: 2 | All |  | Submitted
D7.2 | Plan for Exploitation and Dissemination of Results | Deliverable | IWES | 6 | 6 | 2025 May: 2 | All |  | Submitted
| Legend |  |  |  |  | 2025 Jan: Work Package; 2025 Aug: Task
[18 empty] | Milestone |  |  |  | 1
| M | Milestone | 1
| D | Deliverable | 2
| T | Task
| W | Work package
Members
HAW
IWES
eRoots
UM
UPC
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: D3.1 Requirements for MTI Models / Most critical nonlinearities --> input for WP1